## Sprint Report_MTN_SDK_Arpith
ID | Title | Work Item Type | State | Priority | Effort | Assigned To | Iteration Path | Created Date | Changed Date | Parent | Tags
318745 | Onboard ZM and BN for the staff portal features | Product Backlog Item | Done | 2 | 8 | Muhammed Akoojee Fintech MTN Group <Muhammed.Akoojee@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2/24/2026 7:54:52 PM | 7/16/2026 1:37:07 PM | 318649 | SDK; SDK - ECW; SDK - External Integration
318649 | New OpCo Onboarding | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2/24/2026 1:26:44 PM | 2026-02-04 18:48 | 318647
335548 | Enable ECW stubbing on the SDK layer E2E tests | Product Backlog Item | Committed | 2 | 5 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-10-03 16:56 | 7/14/2026 7:37:16 PM | 175771 | SDK; SDK - Package; SDK - QoL
175771 | General Technical Items | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 7/23/2025 4:11:03 PM | 2026-02-04 18:48 | 118742 | SDK
321814 | Add the ability to stub ECW when running E2E tests | Product Backlog Item | Done | 2 | 13 | JP Strydom <Johannes.Strydom@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 24 | 2026-02-03 18:14 | 2026-02-04 18:48 | 175771 | Consumer; SDK
403619 | Testing of PREPROD - 1.13.0 build - CDI (Electricity & Water Bills ) | Product Backlog Item | In Testing | 2 | 2 | Skho Ntuli Fintech MTN Group <Skho.Ntuli@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-02-06 23:16 | 7/20/2026 8:18:29 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
221687 | Overall SDK Regression and Bugs | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2025-08-10 14:14 | 2026-02-04 18:48 | 118742 | Consumer; QA; SDK
396441 | PRE-PROD BUG : CDI - Make water bill payment api returns transaction id as 'null' | Bug | Done | 4 | 2 | Wesley Chetty Fintech MTN Group <Wesley.Chetty@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 30 | 5/20/2026 3:27:46 PM | 6/23/2026 4:52:34 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
403574 | PRE-PROD BUG : CDI - 'Get Electricity Bill Payment Quote' does not validate on Bill Identifier and Request passes without mandatory Bill Amount option | Bug | Done | 3 | 2 | Kgolagano Matlapeng Fintech MTN Group <Kgolagano.Matlapeng@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 31 | 2026-02-06 18:18 | 6/23/2026 4:51:53 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
403700 | PRE-PROD BUG : CDI - 'Get Electricity Information' - API does not return BillPayment ID | Bug | Done | 3 | 2 | Tshepang Ramonyadiwa Fintech MTN Group <Tshepang.Ramonyadiwa@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 32 | 2026-03-06 13:57 | 6/29/2026 7:37:48 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
427909 | CDI - Customer Name consists of additional info for 'Get Electricity Information' prepaid response | Bug | Done | 3 | 1 | Tshepang Ramonyadiwa Fintech MTN Group <Tshepang.Ramonyadiwa@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 33 | 6/30/2026 1:01:10 PM | 2026-01-07 18:06 |  | Consumer; SDK; Wave 2
464631 | 'Get Elec Bill Information PREPROD CDI' - Returns "No electricity bill response was returned" error on SDK but on the APP proceeds to transact | Bug | Done | 3 | 2 | Kori Sefeane Fintech MTN Group <Kori.Sefeane@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-10-07 13:36 | 7/23/2026 7:20:20 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
480137 | PREPROD BUG CDI - 'Get Electricity Bill Information' - Response for valid identifier is 'Feature error' Postpaid path | Bug | New | 3 | 2 |  | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/20/2026 10:09:02 PM | 7/21/2026 2:43:56 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
480138 | PREPROD BUG: CDI - 'Get Electricity Bill Payment Quote' and "Make electricity payment" - returns 'FeatureError' Prepaid path | Bug | Approved | 3 | 3 | Tshepang Ramonyadiwa Fintech MTN Group <Tshepang.Ramonyadiwa@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/20/2026 10:54:43 PM | 7/22/2026 1:36:17 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
480158 | PREPROD BUG: CDI - 'Make Electricity BillPayment' - returns 'FeatureError' Prepaid path | Bug | Removed | 3 |  |  | Mobile App - Gamification\Internal Projects | 7/20/2026 11:24:46 PM | 7/21/2026 12:30:33 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
481488 | CDI - billAmount not required for prepaid get-electricity-bill-information | Bug | New | 2 | 2 |  | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/21/2026 2:43:27 PM | 7/21/2026 2:44:23 PM | 219364 | Consumer; SDK; SDK - Feature; SDK - QA; Wave 2
481512 | PRE-PROD BUG : CDI - 'Get Electricity Bill Information' - response does not return customername paramater required | Bug | New | 3 |  |  | Mobile App - Gamification\Internal Projects | 7/21/2026 3:17:33 PM | 7/23/2026 7:12:52 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
406190 | Remove billPaymentID from Cameroon Water Feature | Product Backlog Item | Approved | 2 | 2 | Jaco Visser Fintech MTN Group <Jaco.Visser@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-04-06 16:30 | 7/21/2026 4:23:25 PM | 406009 | SDK - Feature
406009 | TODO/Technical Debt | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2026-04-06 13:07 | 2026-04-06 14:23 | 118742
407929 | Cameroon - Wallet Activation OTP to use Notification Service | Product Backlog Item | Approved | 2 | 3 | Wesley Chetty Fintech MTN Group <Wesley.Chetty@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-08-06 14:27 | 7/16/2026 1:01:38 PM | 407926 | SDK - Feature
407926 | Cameroon - Wallet Activation SMS | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2026-08-06 14:14 | 2026-08-06 14:14 | 340345
408036 | CDI - Wallet Activation OTP to use notification service | Product Backlog Item | Approved | 2 | 2 | Wesley Chetty Fintech MTN Group <Wesley.Chetty@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-08-06 18:17 | 7/16/2026 1:35:35 PM | 407927 | SDK - Feature
407927 | Ivory Coast - Wallet Activation SMS | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2026-08-06 14:14 | 2026-08-06 14:14 | 340345
408038 | Ghana - Wallet Activation OTP to use Notification Service | Product Backlog Item | Approved | 2 | 2 | Wesley Chetty Fintech MTN Group <Wesley.Chetty@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-08-06 18:18 | 7/16/2026 1:01:33 PM | 407928 | SDK - Feature
407928 | Ghana - Wallet Activation SMS | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2026-08-06 14:14 | 2026-08-06 14:14 | 340345
411585 | Obtain metrics for Cameroon Wallet Activation | Product Backlog Item | Approved | 2 | 1 | Jaco Visser Fintech MTN Group <Jaco.Visser@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-12-06 17:00 | 7/15/2026 12:08:39 PM | 407926 | SDK
412963 | Make Wallet to Unlinked Bank Transfer - Success - Failed | Bug | Approved | 2 | 2 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 6/15/2026 7:45:12 PM | 7/14/2026 7:37:31 PM |  | Active; Regression; SDK; SDK - QA; SDK - Testing
364891 | Make Wallet to Unlinked Bank Transfer - Success | Test Case | Design | 2 |  | Themba Ngxola Fintech MTN Group <Themba.Ngxola@mtn.com> | Mobile App - Gamification\Internal Projects | 4/15/2026 10:50:58 AM | 6/15/2026 7:39:46 PM |  | Active; Consumer; Regression; SDK; SDK - QA; smoke; Wave 2
416390 | PRE-PROD BUG : CDI - 'Get Electricity Bill Payment Quote' SDK does not validate on the Bill Amount which is mandatory parameter on CIE Electricity | Bug | Done | 3 | 1 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 6/19/2026 2:53:11 PM | 7/23/2026 1:26:06 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
422047 | Cameroon - Banking Bills Test Case Review | Product Backlog Item | Done | 2 | 2 | Weiming Chen Fintech MTN Group <Weiming.Chen@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 6/23/2026 6:05:12 PM | 7/17/2026 6:44:23 PM | 219363 | SDK - Analysis
219363 | Cameroon SDK MVP2 Regression and Bugs | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2025-07-10 18:38 | 2026-02-04 18:48 | 193183 | Consumer; QA; SDK; Wave 2
428026 | Expose Share User Endpoints in the SDK Package | Product Backlog Item | Committed | 2 | 2 | JP Strydom <Johannes.Strydom@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 6/30/2026 3:27:42 PM | 7/24/2026 2:39:23 PM | 428023 | SDK; SDK - Package
428023 | Share User Authentication Across Tenants | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 6/30/2026 3:21:13 PM | 6/30/2026 3:21:13 PM | 118742
444946 | GH - Unlinked Bank Transfer Validation Feature Layer | Product Backlog Item | Approved | 2 | 2 | Niksha Simney Fintech MTN Group <Niksha.Simney@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-01-07 16:08 | 7/23/2026 6:20:07 PM | 208686 | SDK - Feature
208686 | Ghana - Bank Transfer | Feature | Done | 2 |  |  | Mobile App - Gamification\Internal Projects | 9/26/2025 1:14:23 PM | 2026-02-04 18:48 | 208684 | Consumer; Wave 2
446145 | Onboard Congo B | Product Backlog Item | Done | 2 | 3 | Kori Sefeane Fintech MTN Group <Kori.Sefeane@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-01-07 17:25 | 7/22/2026 1:33:51 PM | 446144 | SDK - Infrastructure
446144 | CONGO B - Infrastructure Setup | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2026-01-07 17:23 | 2026-01-07 17:23 | 446141
447191 | UG - Production Deployment of NS for Wallet Activation SMS | Product Backlog Item | Approved | 2 | 2 | Muhammed Akoojee Fintech MTN Group <Muhammed.Akoojee@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-02-07 19:22 | 7/20/2026 1:37:30 PM | 340346 | SDK - Infrastructure
340346 | Uganda - Wallet Activation SMS | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 3/18/2026 12:07:41 PM | 2026-08-06 14:14 | 340345 | Notifications
459033 | Solar Bills Testing for Uganda- get-solar-bill-information | Product Backlog Item | New | 2 | 2 | Arpith Sreevalsan Fintech MTN Group <Arpith.Sreevalsan@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-07-07 14:11 | 7/16/2026 11:38:04 AM |  | Consumer; Regression; SDK; SDK - QA; Wave 2
461120 | PRE-PROD BUG: UG – Get Solar Bill Information API: Bill Identifier Not Found Returns Null Customer Instead of "Not Found" Response | Bug | Done | 3 | 2 | Wesley Chetty Fintech MTN Group <Wesley.Chetty@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-08-07 17:22 | 7/22/2026 1:44:33 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
461454 | [UG PreProd][Solar Bills] PANDA_SOLAR should be removed from supported provider list following decommissioning | Bug | Done | 4 | 1 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 33 | 2026-09-07 14:41 | 7/14/2026 5:54:53 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
463347 | PRE PROD UG - Get Solar Bill Information - Empty billIdentifier Returns ECW Internal Validation Error Instead of Field Validation Message | Bug | Done | 3 | 2 | Tshepang Ramonyadiwa Fintech MTN Group <Tshepang.Ramonyadiwa@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-10-07 11:24 | 7/16/2026 4:44:48 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
459597 | Testing of PREPROD - 1.12.2 build - GH (Electricity Quote and Payment) | Product Backlog Item | Approved | 2 | 2 | Skho Ntuli Fintech MTN Group <Skho.Ntuli@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-07-07 16:13 | 7/21/2026 1:42:52 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
473576 | GHANA PREPROD - 'Get Electricity Bill Information' - SDK API returns 200Ok but response is empty with no data | Bug | Done | 3 | 2 | Tshepang Ramonyadiwa Fintech MTN Group <Tshepang.Ramonyadiwa@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/15/2026 3:19:49 PM | 7/17/2026 11:05:37 AM | 221687 | Consumer; SDK; SDK - QA; Wave 2
461107 | Solar Bills Testing for Uganda- make-solar-bill-payment in Preprod | Product Backlog Item | New | 2 | 3 | Arpith Sreevalsan Fintech MTN Group <Arpith.Sreevalsan@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-08-07 17:09 | 7/16/2026 11:38:09 AM | 461405 | Consumer; Regression; SDK; SDK - QA; Wave 2
461308 | [UG PreProd][Solar Bills][make-solar-bill-payment] Payment requests fail for all configured solar providers except SOLAR_NOW | Bug | Done | 1 | 2 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-09-07 13:36 | 7/15/2026 9:31:47 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
461405 | [UG PreProd][Solar Bills][D_LIGHT_SOLAR] Account is debited despite make-solar-bill-payment API returning TRANSACTION_NOT_COMPLETED error | Bug | Approved | 2 | 3 | Wesley Chetty Fintech MTN Group <Wesley.Chetty@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-09-07 14:30 | 7/23/2026 3:23:49 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
463018 | Preprod UG - Make Solar Bill Payment - Empty billIdentifier Returns Incorrect Validation Error Message | Bug | Done | 2 | 2 | Jaco Visser Fintech MTN Group <Jaco.Visser@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-10-07 11:16 | 7/20/2026 3:53:04 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
467029 | All OpCos - Account is debited despite API returning TRANSACTION_NOT_COMPLETED error | Bug | Approved | 3 | 5 | Wesley Chetty Fintech MTN Group <Wesley.Chetty@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/13/2026 6:56:49 PM | 7/23/2026 3:23:49 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
464735 | Align merchant payment type to momopay | Product Backlog Item | Done | 2 | 2 | Tshepang Ramonyadiwa Fintech MTN Group <Tshepang.Ramonyadiwa@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-10-07 14:47 | 7/22/2026 7:00:42 PM | 257913 | SDK
257913 | Additional Development Work | Feature | In Progress | 2 |  |  | Mobile App - Gamification\Internal Projects | 11/26/2025 4:46:51 PM | 2026-02-04 18:48 | 118742 | Consumer; SDK
465123 | Support Dynamic ECW Context Resolution & Polymorphic User Authentication across Business & Consumer Segments | Product Backlog Item | Done | 2 | 13 | JP Strydom <Johannes.Strydom@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-10-07 17:30 | 7/21/2026 6:35:20 PM | 175771 | SDK; SDK - API; SDK - External Integration; SDK - Feature; SDK - Package
465124 | Remove Axios dependency from the SDK package in favor of native fetch | Product Backlog Item | Done | 2 | 8 | JP Strydom <Johannes.Strydom@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 2026-10-07 17:41 | 7/16/2026 7:27:20 PM | 175771 | SDK; SDK - Package
465598 | Solar Bills Testing for Uganda -get-solar-bill-payment-quote | Product Backlog Item | New | 2 | 2 | Arpith Sreevalsan Fintech MTN Group <Arpith.Sreevalsan@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/13/2026 11:04:21 AM | 7/16/2026 11:38:14 AM |  | Consumer; Regression; SDK; SDK - QA; Wave 2
466996 | Pre-Prod (Uganda): GET /get-solar-bill-payment-quote returns 400 Bad Request for supported solar providers instead of returning a payment quote | Bug | Done | 2 | 2 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/13/2026 5:56:06 PM | 7/15/2026 9:29:21 PM | 221687 | Consumer; Regression; SDK; SDK - QA; Wave 2
473481 | Testing of PREPROD - 1.12.2 build - GH ( Make Water Bill Payment) | Product Backlog Item | Approved | 2 | 2 | Skho Ntuli Fintech MTN Group <Skho.Ntuli@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/15/2026 12:30:06 PM | 7/21/2026 1:42:54 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
473490 | Create required string schema | Product Backlog Item | New | 2 | 3 |  | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/15/2026 1:08:32 PM | 7/16/2026 5:00:50 PM | 406009 | SDK; SDK - API
473610 | UG- Water Bill- Test the get-water-bill-information | Product Backlog Item | In Testing | 2 | 2 | Arpith Sreevalsan Fintech MTN Group <Arpith.Sreevalsan@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/15/2026 5:11:03 PM | 7/16/2026 7:19:35 PM |  | Consumer; Regression; SDK; SDK - QA; Wave 2
474252 | Pre-Prod (Uganda): POST /get-water-bill-information returns a negative billAmount.amount for valid UWSS/NWSC postpaid accounts | Bug | Removed | 2 | 2 |  | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/16/2026 11:21:55 AM | 7/16/2026 1:41:24 PM | 221687 | Consumer; Regression; SDK; SDK - QA; Wave 2
474253 | Pre-Prod (Uganda): POST /get-water-bill-information returns empty customerName and billAmount for valid UWSS/NWSC accounts | Bug | Done | 2 | 2 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/16/2026 11:30:53 AM | 7/23/2026 3:22:41 PM | 221687 | Consumer; Regression; SDK; SDK - QA; Wave 2
474254 | Pre-Prod (Uganda): POST /get-water-bill-information returns an empty success response for invalid bill identifiers (UWSS/NWSC) | Bug | Done | 2 | 2 | Richard Oudejans MTN South Africa <Richard.Oudejans@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/16/2026 11:37:00 AM | 7/21/2026 2:25:54 PM | 221687 | Consumer; Regression; SDK; SDK - QA; Wave 2
473714 | CDI - Water Test Case Review | Product Backlog Item | Done | 2 | 2 | Weiming Chen Fintech MTN Group <Weiming.Chen@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/15/2026 7:22:50 PM | 7/21/2026 12:24:50 PM | 219364 | SDK - Analysis
219364 | Ivory Coast SDK MVP2 Bugs | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 2025-07-10 18:39 | 2026-02-04 18:48 | 193184 | Consumer; QA; SDK; Wave 2
473715 | CDI - Electricity Test Case Review | Product Backlog Item | Done | 2 | 2 | Weiming Chen Fintech MTN Group <Weiming.Chen@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/15/2026 7:23:09 PM | 7/22/2026 2:50:31 PM | 219364 | SDK - Analysis
473716 | CDI - TV Test Case Review | Product Backlog Item | Approved | 2 | 2 | Weiming Chen Fintech MTN Group <Weiming.Chen@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/15/2026 7:23:27 PM | 7/20/2026 3:03:47 PM | 219364 | SDK - Analysis
474311 | Add Merchant Beneficiary - Feature layer | Product Backlog Item | New | 2 | 3 |  | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/16/2026 1:56:33 PM | 7/16/2026 4:31:43 PM | 277375 | SDK - Feature
277375 | Additional Beneficiaries Development | Feature | In Progress | 2 |  |  | Mobile App - Gamification\Internal Projects | 2026-09-01 12:32 | 2026-02-04 18:48 | 118742 | Consumer; SDK
474312 | Add Merchants to Beneficiaries endpoints API and SDK layer | Product Backlog Item | New | 2 | 2 |  | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/16/2026 1:57:37 PM | 7/16/2026 7:26:13 PM | 277375 | SDK - API; SDK - Package
478150 | GH - Startimes Get TV information SDK response is incorrect | Bug | Approved | 2 | 2 | Kori Sefeane Fintech MTN Group <Kori.Sefeane@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/17/2026 3:24:29 PM | 7/23/2026 1:22:38 PM | 478148 | Consumer; SDK; SDK - Feature; Wave 2
478148 | GHANA - MVP2 Regression Testing | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 7/17/2026 3:20:44 PM | 7/17/2026 3:20:44 PM | 208684
479083 | Testing of PREPROD - 1.12.2 build - GH (TV Bills - DSTV) | Product Backlog Item | Approved | 2 | 2 | Skho Ntuli Fintech MTN Group <Skho.Ntuli@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/20/2026 3:39:55 PM | 7/21/2026 1:43:11 PM | 221687 | Consumer; SDK; SDK - QA; Wave 2
480045 | GHANA DSTV URLS - URLS are hardcoded and need to be converted to environment yamls | Product Backlog Item | Approved | 3 | 2 | Niksha Simney Fintech MTN Group <Niksha.Simney@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/20/2026 4:17:27 PM | 7/23/2026 5:57:38 PM | 221687 | Consumer; SDK; Wave 2
480075 | Pre-Prod: POST /get-electricity-bill-information returns an empty success response for an invalid account number for all the UG providers | Bug | Approved | 2 | 3 | Richard Oudejans MTN South Africa <Richard.Oudejans@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/20/2026 6:59:01 PM | 7/22/2026 1:35:23 PM |  | Consumer; Regression; SDK; SDK - QA; Wave 2
480257 | DO NOT PICK UP YET - Pre-Prod (Uganda): POST /get-electricity-bill-information does not return customerName and billAmount.amount for valid electricity accounts (UEDCL, SECL, WenreCo) | Bug | Removed | 2 | 2 |  | Mobile App - Gamification\Internal Projects | 7/21/2026 12:08:39 PM | 7/22/2026 12:26:44 PM |  | Consumer; Regression; SDK; SDK - QA; Wave 2
481511 | Remove "Region" parameter for water bill endpoints - Feature layer | Bug | Approved | 2 | 2 | Michael Paulinus Fintech MTN Group <Michael.Paulinus@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/21/2026 3:11:32 PM | 7/23/2026 3:24:04 PM | 481489 | Consumer; SDK; SDK - API; SDK - Feature; SDK - Package; SDK - QA
481489 | UGANDA - Regression Testing and Bugs | Feature | New | 2 |  |  | Mobile App - Gamification\Internal Projects | 7/21/2026 2:46:39 PM | 7/21/2026 2:46:39 PM | 236102
484790 | Address Sonar Issues | Product Backlog Item | Done | 2 | 2 | JP Strydom <Johannes.Strydom@mtn.com> | Mobile App - Gamification\Internal Projects\Sprint 34 | 7/21/2026 6:51:51 PM | 7/22/2026 5:06:15 PM | 175771 | SDK