## Issues
External ID | Title | Type | Status | Priority | Assignee Email | Story Points | Sprint Name | Sprint Start Date | Sprint End Date | Created Date | Last Updated | Status Changed On | Parent / Epic | Labels
SAMP-101 | User can reset password via email | Story | Done | High | Apoorva.Joshi_EXT@ccm.com | 5 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-20 | 2026-06-01 | 2026-06-01 | SAMP-50 | auth
SAMP-102 | Add audit log for admin actions | Task | Done | Medium | Ratheesh.R_EXT@myccmortgage.com | 3 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-21 | 2026-06-02 | 2026-06-02 | SAMP-50 | audit
SAMP-103 | CSV export of audit log | Story | QA | Medium | Sweta.Das@ccm.com | 3 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-23 | 2026-06-02 | 2026-06-02 | SAMP-50 | audit;export
SAMP-104 | Search audit log by user | Task | QA | Low | Yash.Suthar@ccm.com | 2 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-24 | 2026-06-02 | 2026-06-02 | SAMP-50 | audit
SAMP-105 | Pagination for dashboard widgets | Story | In Review | Medium | Apoorva.Joshi_EXT@ccm.com | 5 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-25 | 2026-06-02 | 2026-06-02 | SAMP-60 | dashboard
SAMP-106 | Dark mode for settings page | Story | In Progress | Low | Ratheesh.R_EXT@myccmortgage.com | 5 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-26 | 2026-06-02 | 2026-05-30 | SAMP-61 | ux
SAMP-107 | Reduce dashboard initial payload | Task | In Progress | High | Sweta.Das@ccm.com | 8 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-26 | 2026-06-02 | 2026-05-29 | SAMP-60 | perf
SAMP-108 | Replace bcrypt with argon2 | Task | In Progress | High | Yash.Suthar@ccm.com | 5 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-27 | 2026-06-02 | 2026-05-31 | SAMP-50 | security
SAMP-109 | SSO with Okta — waiting on tenant creds | Story | Blocked | High | Apoorva.Joshi_EXT@ccm.com | 8 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-28 | 2026-06-02 | 2026-06-02 | SAMP-62 | sso;blocked
SAMP-110 | Add rate limiting on /api/auth | Task | To Do | Medium | Ratheesh.R_EXT@myccmortgage.com | 3 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-29 | 2026-05-29 |  | SAMP-50 | security
SAMP-111 | Documentation pass on auth endpoints | Task | To Do | Low | Sweta.Das@ccm.com | 2 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-30 | 2026-05-30 |  | SAMP-50 | docs
SAMP-112 | Investigate flaky test in CI | Spike | To Do | Medium | Yash.Suthar@ccm.com | 2 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-30 | 2026-05-30 |  |  | ci
SAMP-113 | Dashboard charts misaligned on Safari | Bug | In Progress | Medium | Apoorva.Joshi_EXT@ccm.com | 2 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-31 | 2026-06-02 | 2026-06-01 | SAMP-60 | safari;ui
SAMP-114 | Audit log timestamp shows UTC instead of local | Bug | Done | Low | Ratheesh.R_EXT@myccmortgage.com | 1 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-05-31 | 2026-06-02 | 2026-06-02 | SAMP-50 | audit;tz
SAMP-115 | 500 on POST /users when email is empty | Bug | QA | High | Sweta.Das@ccm.com | 1 | Sprint 12 | 2026-05-26 | 2026-06-06 | 2026-06-01 | 2026-06-02 | 2026-06-02 |  | api

## Status History
External ID | From Status | To Status | Changed On | Changed By
SAMP-101 | To Do | In Progress | 2026-05-26 | Apoorva.Joshi_EXT@ccm.com
SAMP-101 | In Progress | In Review | 2026-05-29 | Apoorva.Joshi_EXT@ccm.com
SAMP-101 | In Review | QA | 2026-05-30 | Sweta.Das@ccm.com
SAMP-101 | QA | Done | 2026-06-01 | Sweta.Das@ccm.com
SAMP-102 | To Do | In Progress | 2026-05-27 | Ratheesh.R_EXT@myccmortgage.com
SAMP-102 | In Progress | QA | 2026-06-01 | Ratheesh.R_EXT@myccmortgage.com
SAMP-102 | QA | Done | 2026-06-02 | Sweta.Das@ccm.com
SAMP-105 | To Do | In Progress | 2026-05-28 | Apoorva.Joshi_EXT@ccm.com
SAMP-105 | In Progress | In Review | 2026-06-02 | Apoorva.Joshi_EXT@ccm.com
SAMP-109 | In Progress | Blocked | 2026-06-02 | Apoorva.Joshi_EXT@ccm.com
SAMP-113 | To Do | In Progress | 2026-06-01 | Apoorva.Joshi_EXT@ccm.com