## Task tracking
Task | Assignee | Start Date | End Date | Actual End Date
API call optimisation(user management) | Venkat | 14/8/2026 | 17/8/2026 | 18/8/2026
Add form field validation | Syeda | 2026-11-08 | 14/8/2026 | 18/8/2026
Pagination for team member & project in account section. admin access content | Vamshi | 2026-04-08 | 14/8/2026 | 14/8/2026
can have project dropdown UI change in presentation | Vamshi | 14/8/2026 | 14/8/2026 | 17/8/2026
Programs, admin getting 0 projects for the program which is not assigned - i think instead we can hide it | Vamshi | 19/8/2026 | 20/8/2026 | 24/8/2026
API call optimisation(notification) | Venkat | 17/8/2026 | 19/8/2026 | 21/8/2026
Replace redundancy code related to show new dialog box | Syeda | 18/8/2026 | 20/8/2026 | 20/8/2026
Refactoring actionItems page. | Vamshi | 17/8/2026 | 19/8/2026 | 21/8/2026
eslint error in account context and auth context files | venkat | 19/8/2026 | 19/8/2026 | 21/8/2026
replacing alert with snackbar and changing positions for maintainability. | Syeda | 20/8/2026 | 24/8/2026 | 25/8/2026
create a new url for portfolio presentation create form, edit form , view and presentation modes | Venkat | 20/8/2026 | 24/8/2026 | 24/8/2026
duplicate API call on clicking any account in administration( prefetching next page) | Syeda | 20/8/2026 | 26/8/2026 | 26/8/2026
on saving, searching team member, multiple API calls are happening | vamshi | 21/8/2026 | 24/8/2026 | 25/8/2026
aligning content in http://localhost:5173/retro to left, like other and update the retro form with MUI date and time picker components | venkat | 25/8/2026 | 25/8/2026 | 26/8/2026
align project name in team performance -> board view | vamshi | 25/8/2026 | 25/8/2026 | 25/8/2026
adding breadcrumbs in adminstration> notification | vamshi | 25/8/2026 | 25/8/2026 | 26/8/2026
adding breadcrumbs in management > retro board | venkat | 26/8/2026 | 26/8/2026
Implement total count calculation for members and projects in the account module on the backend | venkat | 26/8/2026 | 27/8/2026
bug during template delete which is referring by some rules in Rule tab. | Syeda | 26/8/2026 | 27/8/2026
In Account Project section: after performing add, edit or delete actions not getting proper data. | Syeda | 27/8/2026
bug fix for project-action Items API failing | vamshi | 27/8/2026

## Sheet1
Issue / Observation | Assignee
We can have forgot password option on login screen
Currently we have empty in password field, instead we can hide the fields and show a btn kind of thing to allow user to update password | Lavanya
We can have edit profile feature | Lavanya
Currently we can select future dates to generate report, it should not allow | Vamshi
Reports -> daily programs -> date validation is pending | Vamshi
In view presentation of paticular resport, has dominating header bar(blue), due to which the above bar is not recognised
In new presentation popup, we don't have save button do we need it? | Syeda
Super user with profile pic is shown on left nav bar at bottom is it needed? | Raviteja
action items -> view -> edit ->add some invalid date and try to edit it, page is showing blank - we can disable the invalid dates in calender itself ( same in account item edit popup as well) | Raviteja
In account items for eye icon, it shows 'view/edit' tooltip, but there is no edit option | Vamshi
In user management, we can also have clear all option outside the filter popup | Raviteja
In administration -> notifications -> new rule -> for role we can have a dropdown | Raviteja
administration -> on changing tab, we should change the breadcrumb also | Syeda
Change password in edit user can be done better | Lavanya
UI change in edit daily presentation (save, cancel button) | syeda
filter ui change in user management | Raviteja

## Sheet2
Issue / Observation | Assignee
Can add sorting in usermanagement columns (user, userId, role) | syeda
we can include status filter in user management | venkat
we can add alert popup on deactivating rule in notification | vamshi
Change delete confirmation box text for deleting rule - "Are you sure you want to delete this rule?" | syeda
Same thing on templates | syeda
we can have a filters(Account, Projects) in Notification -> logs | venkat
Confirmation popup on removing projects in manage projects | lavanya
Administration -> Programs -> Manage owners, email is missing for other users, on Deleting, updating the primary user no confirmation popup | lavanya
When we are in risk board,on refresh it is going back to dashboard | vamshi
http://localhost:5173/action-items?tab=project, http://localhost:5173/action-items?tab=prgram..... queryparam can more specific) | Lavanya
We can add other column filters as well in action item tabs (searching, sorting as well) | venkat
can add success message on completing mapping | lavanya
somewhere we need makesure, the added template exist
When we are in some path on refresh we go back to the main landing page of that base path | lavanya
in user management we are allowed to deactive user, but there is no way to re activate it thr ui
Error on selecting project on presentation " Failed to ...." | vamshi
proper text on delete confirmation popup("please confirm.....") - no more such stmt | lavanya
Administration -> projects -> select any under team member user able to delete team member without any confirmation | VAMSHI
need to confirm, are we allowed to delete primary owner in manage owners - disabled the delete icon for primary user | lavanya